## HITRANS Const
Approximate Construction Start Date | Approximate Duration of Works | NW Structural Maintenance 2004 - 2005 | Description | Estimated Value | Remarks | Council
2004-12-06 08:00 | 3 mths | A83 Auchindrain Ph3 | Reconstruct | 500000 |  | Argyl & Bute
2005-03-01 | 2 mths | A85 Arrivain Ph2 | Reconstruct | 695000 | Subject to conclusion of land discussions | Argyl & Bute
2004-07-07 08:00 | 1 mth | A86 Aberarder Lodge | Overlay | 450000 | Complete | Highland
2004-10-01 | 2 mths | A9 Nuide Ph4 | Reconstruct | 1230000 | On Site | Highland
2004-10-04 08:00 | 4 mths | A86 Inveroy to Spean Bridge Ph2 | Overlay | 750000 | Contract awarded | Highland
2005-01-01 | 3 mths | A9 Nuide Ph3 | Reconstruct | 1230000 | Out to Tender | Highland
2005-01-01 | 2 mths | A9 Berriedale Ph2 | Reconstruct | 350000 |  | Highland
2005-03-21 08:00 | 2 mths | A9 Scrabster | Inlay | 300000 |  | Highland
2005-03-14 08:00 | 3 mths | A87 Varragil to Portree Ph1 | Overlay | 900000 |  | Highland
2005-01-01 08:00 | 2 mths | A84 St Brydes to Lubnaig | Reconstruct | 515000 | Tender report issued 10/12/04 | Stirling
2005-01-01 | 2 mths | A84 Callander/Doune/Kilmahog | Resurface | 500000 |  | Stirling
Approximate Construction Start Date | Approximate Duration of Works | NW Minor Improvements 2004 - 2005 | Description | Estimated Value | Remarks | Council
2005-02-01 08:00 | 2 mths | A82 Stoneymollen R/bt | National Park Gateway - L/scaping | 475000 |  | Argyl & Bute
2005-02-06 | 2 mths | Argyle & Bute Verge Safety Fencing | Safety Fencing | 100000 |  | Argyl & Bute
2004-10-10 08:00 | 2 mths | A835 - Bilingual Signs | Traffic Signs | 550000 | Contract awarded | Highland
2004-10-01 | 2 mths | A9 Clashaig Bends | Road Realignment | 410000 | Near Complete | Highland
2005-03-01 08:00 | 1 mth | A9 Caithness | Removal of retaining wall | 115000 |  | Highland
2005-03-18 08:00 | 1 mth | A82 Achahannet Layby | Layby Construction | 50000 |  | Highland
2005-03-01 | 1 mth | A835 Marybourgh RA Cycleway F/way Link | Cycleway / Footway | 20000 | Subject to conclusion of land discussions | Highland
2005-02-01 | 1 mth | A9 Dalmagarry Bus Layby | Bus Layby | 40000 |  | Highland
2005-02-01 | 1 mth | A82 Glenfintaig Lodge | Culvert Replacement | 100000 | Subject to conclusion of land discussions | Highland
2005-02-01 | 1 mth | A9 Inver Junction (Carryover) | Junction | 101398.64 | Subject to conclusion of land discussions | Highland
2005-02-06 | 1 mth | A85 Methven Ped Xing | Pedestrian Crossing | 30000 |  | Stirling
2005-02-01 | 3 mths | A85 Lochearnhead Footway | Footway/Road widening | 350000 | Subject to conclusion of land discussions | Stirling
Notes:
1. As a Draft Programme, the above is subject to alteration and Scottish Executive overall funding availability.
2. 'As of Right' schemes are excluded.
3. There is no guarentee that individual schemes will be carried on the specific dates, or that completion will occur within financial year 2004/05.
Approximate Construction Start Date | Approximate Duration of Works | NW Bridges 2004 - 2005 | Description | Estimated Value | Remarks | Council
2005-03-01 | 1 mth | A830 Banavie Swing Bridge | Resurfacing | 50000 |  | Highland
2005-01-01 | 4 mths | A86 Cruinnichidh Wall | Wall strengthening | 50000 |  | Highland
2005-03-01 | 2 mths | A9 1360 Cromarty Kumar joints | Joint replacement / Waterproofing | 240000 |  | Highland
2005-03-01 | 12 mths | A82 Lairig Eilde | Bridge Replacement | 2500000 |  | Highland
2005-02-01 | 2 mths | A82 Allt Cumhang Layby | Wall strengthening | 125000 |  | Highland
2005-03-01 | 3 mths | A9 Tay Bridge | Edge Strengthening | 500000 |  | Perth & Kinross
Approximate Construction Start Date | Approximate Duration of Works | NE Structual Maintenence 2004 - 2005 | Description | Estimated Value | Remarks | Council
2005-01-01 | 2 mths | A95 East of Marypark to Pottery | Reconstruct | 645000 |  | Moray
2005-02-01 | 2 mths | A95 Rosarie to Hillockhead | Reconstruct | 390000 |  | Moray
Approximate Construction Start Date | Approximate Duration of Works | NE Minor Improvements 2004 - 2005 | Description | Estimated Value | Remarks | Council
2004-06-24 08:00 | 2 mths | A96 Rumbuch/Bogbain | Drainage | 160000 | Complete | Moray
Notes:
1. As a Draft Programme, the above is subject to alteration and Scottish Executive overall funding availability.
2. 'As of Right' schemes are excluded.
3. There is no guarentee that individual schemes will be carried on the specific dates, or that completion will occur within financial year 2004/05.